## Plan
Integrated Market Opening Plan - 4 March 2015
| 2015 | [11 empty] | 2016 |  |  |  | 2017
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
Key
Ofwat: Licence design and transition
30 March
Parliament dissolves
Purdah
7 May
General Election
Retail market goes live
Defra consults on charging guidance
MAP 2 consultation
MO staff training
System audit
System audit
Develop assurance framework
MAP3 consultation
MAP Final Conclusions (Post-Vendor)
Ofwat policy development ahead of MAP 3
Codes, processes and design authority
MO IT system procurement
IT Systems Build
Commence RETAIL
Sections 1 & 4 and Schedules 1 & 3
SoS issues authorisation to Ofwat
Consult Welsh Ministers on authorisation
Draft transitionals for Schedule 1 (complex)
Lay cross-border regs Negative SI
Consult on cross-border regs
Draft cross-border regs
Commence
power re. cross-border regs
Coordinate with Scottish Government
Commence
licence mods (S.55)
Commence
procedure for granting licences (S.25)
Ofwat open application process
Ofwat: Licence mods consultation
Ofwat: Licence mods implementation
Ofwat finalise licence
Defra publish licence
Defra: consult on draft licence
Ofwat: draft new WSSL licence
Summer 2015
Defra :Consult on exit regs
Lay exit regs
Enhanced affirmative SI
Ofwat: consult on revised GSS
Ofwat: consult on deemed contract
Ofwat: SoLR & SoFR criteria finalised
Lay GSS regs
SI
Ofwat: SoLR criteria and exit application arrangements
Commence EXITS
(necessary sections only)
Charges scheme rule consultation
Publish charges scheme rules
SoS decision on veto
Commence CODES aspects of Schedules 2 & 4
Commence
req to produce code: Interim duties
Final charging guidance
Shadow operation
Appeals system in place
Lay appeals regs Affirmative SI
Consult on appeals regs
Ofwat: Publish code: Interim duties
Commence
remainder
April 2017
Retail exits allowed
Commence RETAIL
remaining parts of Schedules 2 & 4
Dummy data
Internal upload
Business Requirements
Industry: Data preparation and cleansing
Industry procure, design, build and test systems
Industry: Data consistency - alignment with Data Catalogue (DTC)
Industry : Develop Market Opening Assurance Processes
Industry : Ongoing Assurance
Industry: Revise Wholesale Tariffs for Market Opening
SoS sign-off - Go Active
SoS sign-off - Go Live
Data cleanse based on market actuals
Lay final charging guidance
Business Requirements Support
Update & Additional CSDs
Settlement development
Eligibility consultation
Consultation
Defra
Ofwat
Open Water
Companies
Establish MOSL Board and Membership
Chair
INED Directors
MO CEO recruitment
MO Information for HMT
MO Board elected
Licences
Exits
Charges
Codes & Design Authority
MO Procurement & Operations
MOSL Governance & MO Establishment
Transition & data
Consult on full suite of market documents
Publish eligibility guidance
Oct 2016
Regs complete Parly process
SoS decides on exit applications (December)
Draft appeals regs
Revoke
obsolete regs
Companies
Industry : Market Opening Readiness Assurance
Initial charges scheme rule consultation
MAP3
Ofwat licence handover
Codes peer review
Final upload
MO and companies data migration
Test and commission
System audit
Market testing
MO recruitment
MO seek Classification as Private
MOSL decision
Define data specification
Transition plan
Prepare & issue data guidance
Guidance plans for operational capability
Training & culture change guidance
Transition - central support to companies
Communications - engagement with companies and stakeholders
Agree business customer engagement strategy
Business customer engagement and awareness
Support to companies - business planning processes
Codes panel established
Codes panel operational
MO CEO appointed
MO membership charges
Implement market arrangement code
E2E system & operational testing
Programme assurance
Prepare transition plan for publication
Ofwat: Publish guidance & notices
MAP Conclusions (Pre-Vendor)
MO design authority

## Assumptions
# | Assumptions
A.001 | Companies will continue to engage in the same positive and proactive way that they have over the last several months.
A.002 | All parties will monitor delivery against planning milestones and will work together to manage any slippage through a change control process, and keep companies informed.
A.003 | IT Systems - procurement route remains private and contract award is early August 2015. Assumes IT system build complete by September 2016, with six month period for testing and commissioning.
A.004 | Market Operator established and key appointments (Chair) made by April 2015.
A.005 | Assurance framework in place by end of March 2015.
A.006 | Responses to MAP2 are manageable within the development of MAP3.
A.007 | Engagement with industry on plans and requirements is established by early March 2015.
A.008 | Assurance on market readiness is complete by 'Go-Active' milestone.
A.009 | The integrated programme plan will be aligned with the assurance framework, resulting in the identification of a series of gateway decision points.
A.010 | Exit will be available at the point of market opening.
A.011 | MOSL becomes the market operator as originally envisaged.
A.012 | The process of establishing a new government goes smoothly post-election.

## Change control
Ref # | Date Raised | Change Description | Raised By | Assigned to | Change Status | Impact on other workstreams | Date Closed
CH.001 | 24.02.15 | MOSL Board and Membership/Chair/INED Chair/MO CEO Recruitment activities to move back one month. Original dates shown were in error. | OW | MA | Closed | None
CH.002 | 24.02.15 | MO CEO Recruitment activity moved to end of Q1 2016, from December 2015. Original dates shown were in error. | OW | MA | Closed | None
CH.003 | 26.02.15 | Move eligibility consultation to take on board further feedback. | Mat Stalker | Tom Rogers | Closed | Slight reduction to consultation period.
CH.004 | 02.02.15 | Move deemed contract consultation from July to September-November. | Margareta Serfozo-Matharu | Tom Rogers | Closed | Re-profiling of work to aid delivery.
CH.005 | 02.02.15 | Move GSS consultation from July to September-November. | Margareta Serfozo-Matharu | Tom Rogers | More Info | Re-profiling of work to aid delivery. Further information sought.
CH.006 | 04.03.15 | Remove erroneous duplication of application opening milestone | Tom Rogers | Tom Rogers | Closed | None
CH.007
CH.008
CH.009
CH.010
CH.011
CH.012
CH.013
CH.014
CH.015
CH.016
CH.017
CH.018
CH.019
CH.020