## Sheet1
Affinity Water: Accounting for past delivery detailed actions |  |  |  | Affinity Water
Test area | Action reference | Action type | Action | Required date
Accounting for past delivery | AFW.PD.A1 | Required | PR14 Land sales: Affinity Water is required to provide sufficient evidence to support the forecast trajectory in table App9. | 1 April 2019
Accounting for past delivery | AFW.PD.A2 | Required | PR14 Outcome delivery incentives: Affinity Water is required to update its forecast for 2019-20 performance to take account of the actual 2018-19 performance for all its performance commitments. We expect the company to pay particular focus where we found the evidence provided in its business plan for the 2018-20 forecasts to be insufficient which was for: W-A2: Average water use W-A3: Water available for use W-B1: Compliance with water quality standards (mean zonal compliance) W-B2: Customer contacts for discolouration W-C2: Number of burst mains W-A1: Leakage W-C1: Unplanned interruptions to supply over 12 hours | 15 July 2019
Accounting for past delivery | AFW.PD.A3 | Required | PR14 Residential retail: Affinity Water is required to clarify what the correct number of unmetered water customers in 2016-2017 is; and clarify the justification for its table R9 2019-2020 forecast which departs from the previously observed trends. | 1 April 2019
Accounting for past delivery | AFW.PD.A4 | Required | PR14 Totex: Affinity Water is required to provide an explanation on why 2017-18 expenditure values differ in the annual performance report and the submitted business plan table WS15 making corrective changes as appropriate in its annual performance report data or business plan table WS15 data; and provide a detailed and numerically supported explanation to accompany its forecasted performance for years 2018-19 and 2019-20. | 1 April 2019
Accounting for past delivery | AFW.PD.A5 | Required | PR14 Wholesale revenue forecasting incentive mechanism: Affinity Water is required to provide an explanation to support the table WS13 forecasted performance for years 2018-19 and 2019-20. | 1 April 2019
Accounting for past delivery | AFW.PD.A6 | Required | PR14 reconciliations: Further to the actions we have set out to address our concerns over the evidence provided in its business plan for the individual reconciliations, we will require the company to refresh all of its PR14 reconciliations to replace its 2018-19 forecast performance with 2018-19 actual performance and update the evidence for its forecast 2019-20 performance taking into account of the actual 2018-19 performance. | 15 July 2019
Accounting for past delivery | AFW.PD.B1 | Advised | Affinity Water should produce and provide additional evidence that it has identified: • the drivers of its performance past and current outcomes performance, including financial and reputational performance commitments; • lessons learnt from good and poor past and current performance; • the performance gap between current performance and proposed performance in the 2020-25 business plan; and • measures to ensure deliverability of the 2020-25 business plan. | 24 May 2019
Accounting for past delivery | AFW.PD.B2 | Advised | Affinity Water should produce and provide an action plan that sets out: • how Affinity Water will continuously monitor performance against PR14 and PR19 performance commitments, including how this relates to section 3 of the Annual Performance Report and what evidence it will look for beyond itself and the sector; • how Affinity Water will identify drivers of performance and lessons learnt from both good and poor performance; • how Affinity Water will identify measures to improve performance and integrate these into its business; and • how Affinity Water will ensure that this is a continuous rather than one-off process. | 24 May 2019
Accounting for past delivery | AFW.PD.B3 | Advised | Affinity Water should produce and provide additional evidence that it has identified: • the drivers of its complaints handling performance both in terms of the number of complaints and how well complaints are dealt with, • lessons learnt from good and poor past and current performance; • the performance gap between current performance and proposed performance in the 2020-25 business plan; and • the measures planned or already in place to ensure deliverability of the 2020-25 business plan. | 24 May 2019
Accounting for past delivery | AFW.PD.B4 | Advised | Affinity Water should produce and provide an action plan that sets out: • how Affinity Water will continuously monitor performance, including with reference to CCWater analysis and targets, and those related to the delivery of C-Mex, including what evidence and best practice it will look for beyond itself and the sector; • how Affinity Water will identify drivers of performance and lessons learnt from both good and poor performance; • how Affinity Water will identify measures to improve performance and integrate these into its business; and • how Affinity Water will ensure that this is a continuous rather than one-off process. | 24 May 2019