## Actions
Number | Action | Date Raised | Target Date | Owner | Status | Comments
1 | CCW/Ofwat to share the names of other stakeholders on the steering groups with companies. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete | We are in discussion with English and Welsh stakeholders separately: For the England steering group, we are involving: Defra - Kruti Patel EA - Richard Thompson DWI - Nick Adjei NE - Cordelia Spalding, Pippa Langford Citizens Advice - Andy Manning For the Wales steering group, we are involving: Welsh Government - Eifiona Williams NRW - Mark Squire, Geraint Weber, Ruth Johnston DWI - Ann Bunting
2 | CCW/Ofwat to share the slides used at this meeting with steering group members. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete
3 | CCW/Ofwat to check attendees list on calendar invitations for future meetings. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete
4 | CCW/Ofwat to consider the reputational impact of the use of a financial incentive to encourage participation in the research. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete | As incentives have commonly been used in the past, and the research will be branded CCW and Ofwat, we do not believe this will have a reputational impact on companies.
5 | CCW/Ofwat to share the details of the mapping of company sample sizes with the steering group. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete | Proposals for research sample, per company, were shared with companies in the 3 February email (and copied to wider stakeholders separately). Sampling will be covered at the 14 February steering group meeting.
6 | CCW/Ofwat to consider how research can be shared with the Steering Groups. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete | Research materials and reports will be shared within the group and if any further discussion is required, this can be scheduled
7 | CCW/Ofwat to share final Performance Commitment research report as soon as possible. | 14.02.2022 | 14.03.2022 | CCW/Ofwat | In Progress | Expected publication in April. Will share with steering group members.
8 | Ofwat will consider whether the approach to generating ODI rates should be i) included in the draft methodology and/or ii) developed in the context of the collaborative customer research steering group. | 14.02.2022 | 01.06.2022 | Ofwat | In Progress | Ongoing consideration by Ofwat. The steering group will be kept informed as thinking develops.
9 | Ofwat will review data submitted by companies and confirm, by the end of this week, whether a further data request should be issued. | 14.02.2022 | 18.02.2022 | Ofwat | Complete
10 | Ofwat to establish whether the WINEP guidance is public. If so, share with Natural England. | 14.02.2022 | 14.03.2022 | Ofwat | Complete
11 | All companies to consider and advise Ofwat/CCW if they anticipate problems with the timeline for the ODI rates research. | 14.02.2022 | 28. 02.2022 | All | Complete
12 | Ofwat to share draft ITT and collaborative agreement with companies as soon as available. | 14.02.2022 | 14.03.2022 | Ofwat | Complete
13 | Ofwat/CCW to develop a brief to enable customer service staff to i) understand that the fieldwork is underway and ii) encourage customers to participate. | 14.02.2022 | 01.05.2022 | Ofwat/CCW | In Progress
14 | Ofwat/CCW to share draft fieldwork materials as soon as possible e.g., covering letter for PAF sampling approach. | 14.02.2022 | 01.05.2022 | Ofwat/CCW | In Progress
15 | All companies were invited to approach Ofwat/CCW if more specific discussion is needed on key points. | 14.02.2022 | 14.03.2022 | Companies | In Progress
16 | Ofwat/CCW to share peer reviews with the steering group. | 14.03.2022 |  | Ofwat/CCW | In Progress
17 | CCW/Ofwat to review the joint energy characteristics (PSR) to determine if this can be applied to the ODI rates research. | 14.03.2023 |  | Ofwat/CCW | In Progress
18 | Companies to respond to the revised documents by lunch time on Wednesday, highlighting any red flags. | 14.03.2024 | 16.03.2022 | Companies | In Progress
19 | Ofwat to consider when modelling results from the ODI rates fieldwork will be made available to companies. | 14.03.2025 |  | Ofwat | In Progress

## Lists (hidden)
Cancelled
Complete
Deferred
In Progress
Not Started
Waiting on