## Actions
Number | Action | Date Raised | Target Date | Owner | Status | Comments
1 | CCW/Ofwat to share the names of other stakeholders on the steering groups with companies. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete
2 | CCW/Ofwat to share the slides used at this meeting with steering group members. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete
3 | CCW/Ofwat to check attendees list on calendar invitations for future meetings. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete
4 | CCW/Ofwat to consider the reputational impact of the use of a financial incentive to encourage participation in the research. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete | As incentives have commonly been used in the past, and the research will be branded CCW and Ofwat, we do not believe this will have a reputational impact on companies.
5 | CCW/Ofwat to share the details of the mapping of company sample sizes with the steering group. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete | Proposals for research sample, per company, were shared with companies in the 3 February email (and copied to wider stakeholders separately). Sampling will be covered at the 14 February steering group meeting.
6 | CCW/Ofwat to consider how research can be shared with the Steering Groups. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete
7 | CCW/Ofwat to share final Performance Commitment research report as soon as possible. | 14.02.2022 | 14.03.2022 | CCW/Ofwat | Complete
8 | Ofwat will consider whether the approach to generating ODI rates should be i) included in the draft methodology and/or ii) developed in the context of the collaborative customer research steering group. | 14.02.2022 | 01.06.2022 | Ofwat | In Progress | We have set out our proposed policy approach to setting ODI rates in the PR24 draft methodology, see appendix 8 for further details.
9 | Ofwat will review data submitted by companies and confirm, by the end of this week, whether a further data request should be issued. | 14.02.2022 | 18.02.2022 | Ofwat | Complete
10 | Ofwat to establish whether the WINEP guidance is public. If so, share with Natural England. | 14.02.2022 | 14.03.2022 | Ofwat | Complete
11 | All companies to consider and advise Ofwat/CCW if they anticipate problems with the timeline for the ODI rates research. | 14.02.2022 | 28. 02.2022 | All | Complete
12 | Ofwat to share draft ITT and collaborative agreement with companies as soon as available. | 14.02.2022 | 14.03.2022 | Ofwat | Complete
13 | Ofwat/CCW to develop a brief to enable customer service staff to i) understand that the fieldwork is underway and ii) encourage customers to participate. | 14.02.2022 | 01.05.2022 | Ofwat/CCW | Complete
14 | Ofwat/CCW to share draft fieldwork materials as soon as possible e.g., covering letter for PAF sampling approach. | 14.02.2022 | 01.05.2022 | Ofwat/CCW | Complete
15 | All companies were invited to approach Ofwat/CCW if more specific discussion is needed on key points. | 14.02.2022 | 14.03.2022 | Companies | In Progress
16 | Ofwat/CCW to share peer reviews with the steering group. | 14.03.2022 | 11.04.2022 | Ofwat/CCW | Complete
17 | CCW/Ofwat to review the joint energy characteristics (PSR) to determine if this can be applied to the ODI rates research. | 14.03.2022 |  | Ofwat/CCW | Complete | Discussed at 11 April meeting.
18 | Companies to respond to the revised documents by lunch time on Wednesday, highlighting any red flags. | 14.03.2022 | 16.03.2022 | Companies | Complete
19 | Ofwat to consider when modelling results from the ODI rates fieldwork will be made available to companies. | 14.03.2022 |  | Ofwat | In Progress | We are aiming to share a raw survey dataset with companies early in September and modelled estimates when they are ready.
20 | Companies/stakeholders are invited to submit comments on the proposal to Ofwat by the end of this week (w/c 11/04/22) | 11.04.2022 | 16.04.2022 | Companies | Complete
21 | Ofwat to continue to develop the proposal for the Mapping task and finish group and may consult with a subset of companies to explore issues raised in this discussion. | 11.04.2022 | 30.09.2022 | Ofwat | In Progress | We are resuming work on mapping now that the survey is live and Draft Methodology has been published. There is further scoping work to do before giving a more substantive update.
22 | Companies to respond to Ofwat by the end of this week (16.04.2022) with any objections to the proposal. | 11.04.2022 | 16.04.2022 | Companies | Complete
23 | Acceptability and affordability testing will be on the agenda for the next steering group meeting. | 11.04.2022 | 09.05.2022 | Ofwat/CCW | Complete | On 11 July steering group agenda
24 | Ofwat to arrange steering group meetings from June 2022 onwards | 11.04.2022 | 01.06.2022 | Ofwat | Complete
25 | Ofwat/CCW/Accent/PJM will consider whether to repilot the original design [for ODI rates research], with revised pivots as part of the second pilot | 9.5.2022 | 20.5.2022 | Ofwat/CCW | Complete
26 | Ofwat to email the ODI rates research contracts for signing. Companies to reply no later than 15th June. | 13.6.2022 | 15.6.2022 | Ofwat | Complete
27 | Ofwat/CCW to send a tracked changes version of survey materials to companies by the end of w/c 13th June. | 13.6.2022 | 17.6.2022 | Ofwat/CCW | Complete
28 | Ofwat/CCW to share the final versions of the Second pilot results report and Cognitive testing report, once available. | 13.6.2022 | 31.7.2022 | Ofwat/CCW | In Progress
29 | CCW reminded companies about the request for information about affordability/acceptability approaches | 13.6.2022 | 30.6.2022 | Companies | Complete

## Lists (hidden)
Cancelled
Complete
Deferred
In Progress
Not Started
Waiting on