## Actions
Number | Action | Date Raised | Target Date | Owner | Status | Comments
1 | CCW/Ofwat to share the names of other stakeholders on the steering groups with companies. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete
2 | CCW/Ofwat to share the slides used at this meeting with steering group members. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete
3 | CCW/Ofwat to check attendees list on calendar invitations for future meetings. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete
4 | CCW/Ofwat to consider the reputational impact of the use of a financial incentive to encourage participation in the research. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete | As incentives have commonly been used in the past, and the research will be branded CCW and Ofwat, we do not believe this will have a reputational impact on companies.
5 | CCW/Ofwat to share the details of the mapping of company sample sizes with the steering group. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete | Proposals for research sample, per company, were shared with companies in the 3 February email (and copied to wider stakeholders separately). Sampling will be covered at the 14 February steering group meeting.
6 | CCW/Ofwat to consider how research can be shared with the Steering Groups. | 10.01.22 | 14.02.22 | CCW/Ofwat | Complete
7 | CCW/Ofwat to share final Performance Commitment research report as soon as possible. | 14.02.2022 | 14.03.2022 | CCW/Ofwat | Complete
8 | Ofwat will consider whether the approach to generating ODI rates should be i) included in the draft methodology and/or ii) developed in the context of the collaborative customer research steering group. | 14.02.2022 | 01.06.2022 | Ofwat | Complete | We have set out our proposed policy approach to setting ODI rates in the PR24 draft methodology, see appendix 8 for further details.
9 | Ofwat will review data submitted by companies and confirm, by the end of this week, whether a further data request should be issued. | 14.02.2022 | 18.02.2022 | Ofwat | Complete
10 | Ofwat to establish whether the WINEP guidance is public. If so, share with Natural England. | 14.02.2022 | 14.03.2022 | Ofwat | Complete
11 | All companies to consider and advise Ofwat/CCW if they anticipate problems with the timeline for the ODI rates research. | 14.02.2022 | 28. 02.2022 | All | Complete
12 | Ofwat to share draft ITT and collaborative agreement with companies as soon as available. | 14.02.2022 | 14.03.2022 | Ofwat | Complete
13 | Ofwat/CCW to develop a brief to enable customer service staff to i) understand that the fieldwork is underway and ii) encourage customers to participate. | 14.02.2022 | 01.05.2022 | Ofwat/CCW | Complete
14 | Ofwat/CCW to share draft fieldwork materials as soon as possible e.g., covering letter for PAF sampling approach. | 14.02.2022 | 01.05.2022 | Ofwat/CCW | Complete
15 | All companies were invited to approach Ofwat/CCW if more specific discussion is needed on key points. | 14.02.2022 | 14.03.2022 | Companies | In Progress
16 | Ofwat/CCW to share peer reviews with the steering group. | 14.03.2022 | 11.04.2022 | Ofwat/CCW | Complete
17 | CCW/Ofwat to review the joint energy characteristics (PSR) to determine if this can be applied to the ODI rates research. | 14.03.2022 |  | Ofwat/CCW | Complete | Discussed at 11 April meeting.
18 | Companies to respond to the revised documents by lunch time on Wednesday, highlighting any red flags. | 14.03.2022 | 16.03.2022 | Companies | Complete
19 | Ofwat to consider when modelling results from the ODI rates fieldwork will be made available to companies. | 14.03.2022 |  | Ofwat | Complete | Update provided at 11 July meeting. Notes of the meeting included an explanation.
20 | Companies/stakeholders are invited to submit comments on the proposal to Ofwat by the end of this week (w/c 11/04/22) | 11.04.2022 | 16.04.2022 | Companies | Complete
21 | Ofwat to continue to develop the proposal for the Mapping task and finish group and may consult with a subset of companies to explore issues raised in this discussion. | 11.04.2022 | 30.09.2022 | Ofwat | Complete | Updates provided at subsequent steering group meetings.
22 | Companies to respond to Ofwat by the end of this week (16.04.2022) with any objections to the proposal. | 11.04.2022 | 16.04.2022 | Companies | Complete
23 | Acceptability and affordability testing will be on the agenda for the next steering group meeting. | 11.04.2022 | 09.05.2022 | Ofwat/CCW | Complete
24 | Ofwat to arrange steering group meetings from June 2022 onwards | 11.04.2022 | 01.06.2022 | Ofwat | Complete
25 | Ofwat/CCW/Accent/PJM will consider whether to repilot the original design [for ODI rates research], with revised pivots as part of the second pilot | 9.5.2022 | 20.5.2022 | Ofwat/CCW | Complete
26 | Ofwat to email the ODI rates research contracts for signing. Companies to reply no later than 15th June. | 13.6.2022 | 15.6.2022 | Ofwat | Complete
27 | Ofwat/CCW to send a tracked changes version of survey materials to companies by the end of w/c 13th June. | 13.6.2022 | 17.6.2022 | Ofwat/CCW | Complete
28 | Ofwat/CCW to share the final versions of the Second pilot results report and Cognitive testing report, once available. | 13.6.2022 | 31.7.2022 | Ofwat/CCW | Complete
29 | CCW reminded companies about the request for information about affordability/acceptability approaches | 13.6.2022 | 30.6.2022 | Companies | Complete
30 | Accent/PJM Economics to write up the Stage 2 report for circulation to the steering group members. | 11.07.2022 | 15.08.2022 | Accent/PJME | Complete | Link to final report posted on Ofwat webpage
31 | Ofwat/CCW to appoint the contract for the analysis and modelling before the next steering group meeting. | 11.07.2022 | 8.08.2022 | Ofwat | Complete
32 | Steering group members invited to provide more responses to the 'request for information' on affordability and acceptability testing. | 11.07.2022 | 8.08.2022 | Steering group members | Complete
33 | CCW to check whether it is possible to share details of agencies approached to provide input to development of a common approach to affordability and acceptability testing. | 11.07.2022 | 8.08.2022 | CCW | Complete | Steering group members are aware of the people/agencies involved in the Ofwat/CCW development project for affordabiity and acceptability testing
34 | South West Water offered to share information about the WaterShare+ panel | 11.07.2022 | 8.08.2022 | South West Water | Complete
35 | Ofwat/CCW to give extended notice of the next steering group's agenda. | 11.07.2022 | 8.08.2022 | Ofwat/CCW | Complete
36 | Re mapping: Ofwat to consider the timing/volume of information requests in line with the other responsibilities of companies at this time. | 8.08.2022 | 12.09.2022 | Ofwat | Complete
37 | Re ODI rates research update: CCW to circulate slides used during the presentation. | 12.09.2022 | 19.09.2022 | Ofwat/CCW | Complete
38 | Re Mapping: Ofwat to reply to companies on whether a data request and data submission timeline can be produced. | 12.09.2022 | 10.10.2022 | Ofwat | Complete
39 | Re Affordabiity and acceptability testing: Companies to send CCW examples of a breakdown of the average bill to compare their formats. | 12.09.2022 | 10.10.2022 | Companies | Complete
40 | Re Affordability and acceptability testing: Companies were invited to reply to a series of questions related to implementation of a standardised research approach (set out in an email sent by CCW on 13.10.2022 | 12.09.2022 | 10.10.2022 | Companies | Complete
41 | Re ODI rates research household dataset: Ofwat to share dataset with companies | 10.10.2022 | 14.10.2022 | Ofwat | Complete
42 | Re ODI rates research Ofwat to circulate a report on the household and non-household fieldwork providing a full account of the sampling methodology and approach (including anonymisation, weighting etc), reporting of survey findings, as well as the survey materials. | 10.10.2022 | 30.11.2022 | Ofwat | In Progress
43 | Re affordability and acceptability testing: companies invited to share examples of research which includes treatment of inflation | 10.10.2022 | 14.11.2022 | Companies | Complete
44 | Re affordability and acceptability testing: Ofwat to arrange smaller meetings with companies, to discuss points related to the guidance for affordability and acceptability testing, if needed. | 10.10.2022 | 16.12.2022 | Ofwat | In Progress | Meetings to be held with companies to gather views on the draft affordability and acceptabililty guidance on 23 and 24.11.2022.
45 | Re Non-household dataset: further information is to be provided about 'other' survey responses; Accent will backcode these and then share the dataset with companies | 14.11.2022 | 25.11.2022 | Accent/PJME | In Progress
46 | Re Non-household dataset: Companies to email Accent (Julian Hollo-Tas) to gain access to the raw data (anonymised and unweighted) if they have different details to that supplied to access the household dataset | 14.11.2022 | 25.11.2022 | Accent | In Progress
47 | Re: The slides for the presentations on non-household fieldwork (by Accent/PJME) and econometric modelling (PJME), to be provided to steering group members | 14.11.2022 | 22.11.2022 | Accent/PJME | Complete
48 | Re ODI rates research: the final report of the ODI Rates Research fieldwork will be circulated by mid-December. | 14.11.2022 | 16.12.2022 | Ofwat | In Progress
49 | Re ODI rates research: Accent to provide information about how long the fieldwork had taken and response rates for different amounts of follow up i.e. first contact, then first and second reminders. | 14.11.2022 | 16.12.2022 | Accent | In Progress
50 | Re ODI Rates research: Ofwat to provide a defintion of the relevant performance commitments, including spillages (and whether they related to the number or duration). | 14.11.2022 | 13.12.2022 | Ofwat | In Progress
51 | Re ODI Rates research: Ofwat to consider whether it can provide more information about the mapping, especially for the second batch of performance commitments, which might take the form of detailed annexes giving the underlying equations. | 14.11.2022 | 12.12.2022 | Ofwat | In Progress
52 | Re affordability and acceptability testing: Ofwat to develop a matrix on approaches for water and wastewater companies when testing bill amounts, where customers receive services from water and wastewater companies. | 14.11.2022 | 25.11.2022 | Ofwat | In Progress | To be discussed with companies at the engagement meetings on affrodability and acceptability guidance (23 and 24.11.2022).

## Lists (hidden)
Cancelled
Complete
Deferred
In Progress
Not Started
Waiting on